## Author
Author | Date | Type | version
Rishabh | 2020-02-04 | Initial Draft | 0.1
Rishabh | 15/4/2020 | Updated Efforts | 0.2
Sayali | 15/4/2020 | Efforts added | 0.2
Tejaswi | 15/4/2020 | Efforts added | 0.2

## Over Efforts
DETAILS | SFDC | UI/UX | MOBILITY
Requirement Analysis | 6 | 3 | 1
Development | 19 | 4 | 27
Testing | 6 |  | 1
DEPLOYMENT | 1.5 |  | 1
TOTAL | 32.5 | 7 | 30
| SR_OptiMUSSouth_TWM_728 | SR2
Scope for Picklist | 175 | 215
Scope for validation
RA
dev
test script
peer testing
promote to UAT
Uat test
Deployment

## Salesforce Efforts
S.No | Tasks | Dev Efforts
1 | Creation of objects , fields, pagelayouts,history tracking,validations | 1
2 | Creation of same objects on South with same validations | 1
3 | Generation of pdf on button click | 0.5
4 | To Re-Process the record (Salesforce to Salesforce) on button click | 0.75 |  | * code review is included in this.
5 | S2S Connection (Central to South) includes mapping of fields objects and trigger creation | 2
6 | Creation of profiles/persmissions | 2
7 | Creation of Api's to Connect with the mobile app | 7 | 5/6 apis approx 1 day each
7.1 | Personnel Info Sending to Mobile Api
7.2 | Sending Questions/ answer data to Mobilse Api
7.3 | Getting Response from the app.
7.4 | Updation/insertion of Questions
7.5 | Scheduler / Button to update logic at mobile end
8 | Validation Rule for the mobile side inside to the salesforce | 2
9 | Automated Emails/ Email Services/Oracle Integration | 2.75
19

## UI UX Efforts
S.No | Tasks | Dev Efforts
1 | Requirement Gathering | 1
2 | Wireframe creation | 1
3 | Clickable Prototype through wireframe | 2
4 | Icongraphy and Visual Design (Color) | 3
| Total | 7 Days

## Mobility Efforts
Functionality | Description | Efforts(Days)
Project Setup | Project and environmental setup | 1
QR Login | QR Login with design and API | 1.5
Input Form | Get Details Screen (Name, Reg Number., Driver Mate Name, Job No(May have QR), Location(Current Location)) | 2
Questions Screen | Status Questions (Have you signed in?, Purpose of Visit) | 1.5
Dashboard Screen | Will have List of Previous RA, Option to create RA, Update RA, View RA | 1
Offline Database | Databse Creation and Implementation | 2
Create RA | API to get all the questions from Salesforce and save it to database | 1
| UI and Validations | 1
| Screens Flows (Dynamic Next Question or activity is dependent on the answer of the current Question, it can have multiple flows and usecases) | 2
Submit RA | Take 1 Mandatory and 2 Optional Photos UI and Implementation | 1.5
| Save Data in Database | 1.5
| Agree Terms and Conditions, Complete Risk Assessment with Date & Time, Location send it to API | 1.5
Offline Functionality | Check for Internet Connection, Once Connection is active send the pending data to Salesforce | 2
View RA | PDF Structure Creation | 2
| Show all the Answers and Photos saved for each RA in PDF generated locally in device. | 1.5
Update RA | Prefill existing saved Answers, and update the RA | 2
List RA | Show List of Previously submitted RA | 1
Integration Testing | Salesforce Side Integration Testing | 1
| Total | 27