## MTS Appstore Changes
Please see details of change request for MTS App Store Mobile App
1. Please redesign the user interface to new design (PDF attached seperately)
1.a) Existing Design |  |  |  | 1.b) New Design
The new design image 1.b will be the new home page and should replace the existing design image 1.a
The icons at the top of the page from left to right represent the following
Home Page
Universal Search Bar
Whats New
Profile
The icons at the bottom of the screen from left to right represent the following
Internal Apps
External Apps
Useful Files
Useful Links
Help & Support
2. When you click on any of the icon the top banner with company logos and the icons should remain on the page but only the middle section of the page change as per the content of what icon is clicked
(We will mange the content of what is displayed for the following tabs through the admin view - Whats New, Internal Apps, External Apps, Usefule Files and Useful Links)
2.a) On the Profile page please add name of user and Sign Out button
2.b) On Help & Support page please add message 'For any Help or Support queries please email BT.OptiMUS@morrisonts.co.uk' and add link to email if possible
2.c) The What New page we contain details of when apps have been updated (Version number, Version History, date updated & description of update) the same will apply for any files that are updated
3. The Categories bar should be added to the following tabs showing the categories below, please add this to the top of the page below the home button
Standard categories list |  |  |  |  | View of current design
Internal Apps | External Apps | Useful Files | Useful Links
Health & Safety | Health & Safety | Health & Safety | Health & Safety
Training | Training | Training | Training
Field Services | Field Services | Field Services | Field Services
Business | Business | Business | Business
Top Apps | Top Apps
Recommended For You | Recommended For You
4. In the search bar change the text to Search MTS App Store *Please change text to Search App Store*
5. Current view of Hosted Apps page
5.a) Add Install Now button on the right hand side next to App name and description that take you to the Installl app page, currently you have to click on app name for this
6. Current view of App Install page
6.a) Change text from Screenshots tp Preview
6.b) Change Add Comment to Add Review
6.c) Remove text above Add Comment
6.d) Change text 'Reviews:' to Ratings & Reviews
6.e) Change text at the bottom from Morrison Telecom Services to MTS App Store *Change back to Morrison Telecom Services*
6.f) Change 'Documents:' text to a links icon same as the links icon from home page
6.g) Change' Admin' in Reviews to MTS App Store response *Change to App Store Response*
6.e) Add numeric rating out of 5 similar to below
7. Remove Menu button
8. Install App screen current view
8.a) Can message display MTS App Store would like to install “App Name” *Developers advised this is not achievable*
8.b) Once Install is clicked can we add an installing app image that changes Install button to Installed once it has completed

## Admin View Changes
Please make the following changes to Admin view
1.a) Current design | [6 empty] | 1.b) New Image
1.c) Add logos for Avonline, Magdalene and Morrison Telecom Serives to the top bar same as MTS Appstore view
Change colour theme to match New Image (1.b)
1.d) Change text on the tabs to below and add logos from app view before the text, also add 2 new tabs 'What New' and 'Help/Support' as below with logos from (1.b)
Add New
| Internal Apps | External Apps | Useful Files | Useful Links | Whats New | Help / Support
Add new button 'Add New' which will have same functionality as existing 'Add New Resources' button
Remove 'List of Resources' text and remove Add New Resources button
Add the Home icon in place of Morrison Telecom Services logo using Home Logo supplied
1.e) Change text Admin to Admin View and change settings icon to a Menu icon
Add the following option to Menu list
Category List
Add a new Profile icon to the top bar using the logo supplied add the following options in this list
Reset Password
Sign Out
Change the search bar to the search logo when clicked this should open up the search bar, the text inside the bar should be changed to match the new tab names.
1.f) Change Text at the bottom of the screen to MTS AppStore Admin View *Change back to Morrison Telecom Services*

## Observations
On Mobile View
1. On Filter you cant select more than 1 category
2. No option to clear the Filter
3. When you apply a filter there is no way of knowing which filter you have selected without going back into the Filter icon, can you please display the filter choices at the top of the screen below the Home icon ?
4. User should be able to click on Home icon from any tab (this was discussed in a previous call) this is not working when you are in any of the tabs from the bottom of the screen

## Additional Requirements
Requirements Summary
-Add new functionality to Useful Files tab to allow for Files to be sorted into Folders -There should be standard set of folders (Business, Field Services, Health & Safety & Training) and also the option to create new folders -All Files should be sorted into Folders
-The same file should not be able to be added to multiple Folders
-Custom Folders should have functionality to be made Private and only viewable to Users with permission to view - this should be managed from the Admin View
1. Admin View
2. Change Add New button text to Add New File
3. Create a new button Add New Folder, this should have the following information
Folder Name
Add Files
Folder Type - Public or Private | If Private provide way of making visible to certain group of users
4. Add New view
5. After Description field add option to add to standard list of folders, if User does not want to add to this list provide option to create a new folder from this page
6. Useful Links tab should also be sorted by the following categories
Business
Field Services
Health & Safety
Training
7. Please change App name from MTS App Store to Telecom App Store this needs to be changed in all the places where MTS App Store or Morrison Telecom Services is referenced

## Testing Status
Sr. No. | Requirement | Testing Status | Comments | Planned Completion Date
Admin View - Requirements
1 | 1.a and 1.b) Current design to new design | Passed
2 | 1.c) Add logos for Avonline, Magdalene and Morrison Telecom Serives to the top bar same as MTS Appstore view. Change colour theme to match New Image (1.b) | Passed
3 | 1.d) Change text on the tabs to below and add logos from app view before the text, also add 2 new tabs 'What New' and 'Help/Support' as below with logos from (1.b) Add new button 'Add New' which will have same functionality as existing 'Add New Resources' button. Remove 'List of Resources' text and remove Add New Resources button. Add the Home icon in place of Morrison Telecom Services logo using Home Logo supplied. | Passed | KM[28/01]: "What New" tab is not present. below tabs with logos should be present and order should be maintained. Internal Apps,External Apps,Useful Files,Useful Links,Whats New,Help / Support Dev[28/01]: "What New" will not be present in tabs. It will be managed using "New" button in menu. KM[28/01]: Need confirmation from Shuma. SN[28/01]: "What New" tab should be present. All tabs should be renamed. KM[31/01]: Passed retesting. However, tabs are not in order. "Useful Files" should be before "Useful Links". Also "Internal Apps" and "External Apps" are not plural. KM[03/02]: Passed retesting.
4 | 1.e) Change text Admin to Admin View and change settings icon to a Menu icon. Add the following option to Menu list Category List. Add a new Profile icon to the top bar using the logo supplied add the following options in this list. Reset Password Sign Out Change the search bar to the search logo when clicked this should open up the search bar, the text inside the bar should be changed to match the new tab names. | Passed | KM[27/01]: 1. For requirement - "Add a new Profile icon to the top bar using the logo supplied add the following options in this list." - No profile icon is present. After clicking on Profile icon, below options should be displayed. Profile Icon Options: Reset Password Sign Out "Welcome Admin" Menu should display options - "Category List", "Whats New". 2. Search bar is not changed to Search Logo. KM[31/01]: Passed retesting.
5 | 1.f) Change Text at the bottom of the screen to MTS AppStore Admin View | Passed | KM[28/01]: Text "MTS App Store" is not present at the bottom of the screen. SN[28/01]: Text should be "Telecom Devision App Store Admin View" JM[29/01]: Text is changed for Admin - "Telecom Devision App Store Admin View" KM[29/01]: Passed retesting.
6 | Search Text for External Apps should be "Search External Apps". Currently, "s" (Plural) is missing in "Apps". | Ready to be reviewed
Non-Admin View - Requirements
1 | 1. Please redesign the user interface to new design (PDF attached seperately) 1.a) Existing Design to 1.b) New Design The new design image 1.b will be the new home page and should replace the existing design image 1.a The icons at the top of the page from left to right represent the following Home Page Universal Search Bar Whats New Profile The icons at the bottom of the screen from left to right represent the following Internal Apps External Apps Useful Files Useful Links Help & Support | Passed
2 | 2. When you click on any of the icon the top banner with company logos and the icons should remain on the page but only the middle section of the page change as per the content of what icon is clicked (We will mange the content of what is displayed for the following tabs through the admin view - Whats New, Internal Apps, External Apps, Usefule Files and Useful Links) 2.a) On the Profile page please add name of user and Sign Out button 2.b) On Help & Support page please add message 'For any Help or Support queries please email BT.OptiMUS@morrisonts.co.uk' and add link to email if possible 2.c) The What New page we contain details of when apps have been updated (Version number, Version History, date updated & description of update) the same will apply for any files that are updated | Passed
3 | 3. The Categories bar should be added to the following tabs showing the categories below, please add this to the top of the page below the home button Standard categories list. | Passed | KM[27/01]: Categories List is not present for Non-Admin users to the top of the page. Dev[28/01]: Category List is added to bottom of the page. KM[28/01]: Shuma to confirm if it is OK. JM[31/1] : Unnecessary categoryies are deleted. KM[31/01]: Passed retesting.
4 | 4. In the search bar change the text to Search MTS App Store | Passed | SN[29/01]: Text needs to be changed to "Search App Store" KM[03/02]: Passed retesting.
5 | 5. Current view of Hosted Apps page. 5.a) Add Install Now button on the right hand side next to App name and description that take you to the Installl app page, currently you have to click on app name for this | Passed
6 | 6. Current view of App Install page 6.a) Change text from Screenshots tp Preview 6.b) Change Add Comment to Add Review 6.c) Remove text above Add Comment 6.d) Change text 'Reviews:' to Ratings & Reviews 6.e) Change text at the bottom from Morrison Telecom Services to MTS App Store 6.f) Change 'Documents:' text to a links icon same as the links icon from home page 6.g) Change' Admin' in Reviews to MTS App Store response 6.e) Add numeric rating out of 5 similar to below | Passed | KM[27/01]: 6.e) Change text at the bottom from Morrison Telecom Services to MTS App Store - Text "Morrison Telecom Services" is not displayed. JM[29/01]: Text is changed for Admin as well as Non-Admin - "Telecom Devision App Store" KM[29/01]: Text is still not displayed. SN[29/01]: Text needs to be changed to "Morrison Telecom Services". KM[03/02]: Passed retesting.
7 | 7. Remove Menu button | Passed
8 | 8. Install App screen current view 8.a) Can message display MTS App Store would like to install “App Name” 8.b) Once Install is clicked can we add an installing app image that changes Install button to Installed once it has completed | Future Enhancement | KM[27/01]: Message "MTS App Store would like to install “App Name”" is not displayed. Instead "Do you want to download <<App Name>> is displayed. After installing the app, Install button is not changed to "Installed". It remains as "Install". Dev[28/01]: Message comes from OS. It can't be changed. SN/ KM[28/01]: After installing app, "Install Now" button should change to "INSTALLED". Dev team is looking into it. Under investigation. Difficult to achieve. To be looked as Future development.
Additional Observations:
Admin - Additional Observations:
1 | When Admin User clicks on "Add New" button and then click on "Add New Category", form is displayed to enter Category name. When Admin User enters category name and click Save button, it gives error message "Duplicate Category Name". Similarly, when user clicks on "Edit" button for any app and save Category, "Duplicate Category" message is displayed. Also, list of categories not displayed. | Passed | KM[31/01]: Passed retesting.
2 | When Admin User tries to edit App and add another document, nothing happens upon clicking on Save button. | Passed | KM[29/01]: Passed retesting.
3 | Not able to add new app. Nothing happens after clicking on Save button. It is happening for both Hosted and Third Party Apps, Web page URLs. | Passed | KM[29/01]: Passed retesting.
4 | When User adds a new document, extra characters "%20" are added and number is added at the end. For example - Filename "Accreditation. Third request. Subcontractor.docx" appears as below in MTS Appstore: "Accreditation.%20Third%20request.%20Subcontractor_69_010618.docx" | Passed | JM[30/01] : Removed % character. Just need confirmation - can we have same document name in multiple App? KM[31/01]: Passed retesting. Shuma to confirm about above query by Jayesh. SN[03/02]: Document names can have same name in multiple apps. KM[03/02]: Passed retesting.
5 | Admin Users can see only 10 items on the page. "Next" button is disabled and Page number is also disabled. If app / items count is more than 10, then all items are not visible. This is applicable to all tabs - Hosted Apps, Third Party Apps, Webpage URL, Documents. | Passed | KM[29/01]: Passed retesting.
6 | When Admin User responds to review, it deactivates the review automatically. Active checkbox becomes unchecked. | Passed | KM[31/01]: Passed retesting.
7 | Incorrect Ratings next to App Icon. In Ratings & Reviews, it shows 4.5 stars but in ratings next to App icon shows only 4 stars. | Passed | KM[29/01]: Passed retesting.
8 | "Iphone Package Name:" and "iPad Package Name:" can be removed from Internal Apps page. It is not used anywhere. | Passed | KM[31/01]: Failed retesting. "Iphone Package Name:" and "iPad Package Name:" are still present on Admin View for Internal Apps. KM[03/02]: Passed retesting.
9 | There should be possibility for admin users to add App Icon / Logo for “External Apps” same as for “Internal Apps” and logo should be displayed to non-admin/Admin users against the app. | Passed | KM[29/01]: It was requested in the old version of MTS Appstore. KM[03/02]: Passed retesting.
10 | There should be possibility for admin users to add screen shots in “External Apps” same as for “Internal Apps” and screen shots should be displayed to non-admin users. | Passed | KM[29/01]: It was requested in the old version of MTS Appstore. KM[03/02]: Passed retesting.
11 | When there are multiple files in one of the "Useful Files" and admin user delete one of the files it still displays deleted file with name "undefined". (31/01) | Passed | KM[03/02]: Passed retesting.
Non Admin - Additional Observations:
1 | For "External Apps", there is "INSTALL NOW" button. When Non-Admin user clicks "INSTALL NOW" button, nothing happens. When Non-Admin user clicks on "INSTALL NOW" button, it should take non-admin user to installation page. | Passed | Dev / SN: "INSTALL NOW" button on External apps to be removed next to app icon for non admin users. KM[29/01]: Passed retesting.
2 | iPad, iPhone and Tablet builds are not yet available for testing. | Passed | KM[29/01]: iPad and iPhone build provided but they can't be installed. Tablet build is still not available. KM[31/01]: Unable to install MTS Appstore on iPad, iPhone and Tablet. KM[03/02]: Passed retesting. MTS Appstore Staging is installed on iPad, iPhone and Tablet.
3 | On Filter you can't select more than 1 category | Future Enhancement
4 | No option to clear the Filter. | Passed | KM[31/01]: Option to clear filter is present.
5 | When you apply a filter there is no way of knowing which filter you have selected without going back into the Filter icon, can you please display the filter choices at the top of the screen below the Home icon ? | Passed | KM[31/01]: Selected category Name is present but category name is squashed. Sent details and screen prints in separate email. KM[03/02]: Passed retesting.
6 | User should be able to click on Home icon from any tab (this was discussed in a previous call) this is not working when you are in any of the tabs from the bottom of the screen | Passed
7 | Only one “External App” URL should be displayed to non-admin users based on the device they are using. | Passed | KM[29/01]: It was requested in the old version of MTS Appstore. KM[31/01]: Passed retesting.
8 | When user clicks on link in "Useful Links", link should open in a new tab. Currently, it is opening in the same tab. | Passed | Dev[31/01]: Need new Requirements. KM[03/02]: Passed retesting.
9 | iPad - Unable to install Internal App using "INSTALL NOW" button next to App Name. It gives error - "No link available for mac". When user opens App details, "Install" button is not present eventhough iOS build is hosted by Admin User. (iPad version: 10.3.4 (14G61), iPad Model: MD522B/A) | Ready to be reviewed | KM[31/01]: Sent details and screen prints in separate email.
10 | Logos need to be aligned correctly for non-admin users as discussed in meeting on 03/02/2020. | Ready to be reviewed
11 | iPhone - Unable to install apps using "INSTALL NOW" button. | Ready to be reviewed
12 | When "MTS App Store" is idle for some time, it gets logged out and show Login form with Username and Password. As only QR code scan login is allowed, login form should not be displayed. Dev team to look into it and come up with solution. It was discussed in the meeting on 31/01/2020. | Enhancement | KM/SN[03/02]: What idle time is allowed before application gets logged out?
13 | Android Tablet - "Install" button is not displayed correctly. Only small red box is displayed.(03/02/2020) | Ready to be reviewed
14 | When user install app using "INSTALL NOW" button next to Internal app, count of download does not increase.(03/02) | Failed
15 | When User installs MTS Appstore on iOS device, user needs to trust certificate. Will it happen in Live as well? (03/02) | Query | Dev[04/02]: Users will have to trust certificate in Live as well. AV[04/02]: Asked dev team to automate trusting certificate details. Dev team to check it.
16 | When rating is decimal, then it gets overlapped with stars in External Apps, Useful Files and Useful Links.Rating should allow only one decimal. Currently, it is allowing 3.3333333333333335. This issue is for both Admin and non-admin users. | Failed
17 | When user clicks on Filter button, list of categories displayed. There should be space between Category Name and Radio button. Also, Category Name should be aligned to centre of Radio button. Currently, they are slightly aligned to top of radio button. When user selects category, Category Name is displayed at top. There should be some margin/space between end of screen and Category name. | Failed